Terms of Reference for consultancy Services of

Conflict Mapping and Context Analysis for Luuq District, Gedo region, Jubaland State of Somalia.

Reference #PR 012/ADRO/2026                                                                                                6/05/2026

Access Development and Relief Organization (ADRO) is a women-led humanitarian and development cooperation organization dedicated to peacebuilding, governance and conciliation integrated with life-saving emergency interventions and sustainable development solutions across Somalia. ADRO hereby invites qualified, eligible and experienced Consultancy firms to submit Request for Proposal (RFP) to undertake a systematic conflict mapping and context analysis in Luuq distict, Gedo region, Jubaland State of Somalia.

- Background and Context

Somalia has faced decades of fragmentation, political instability and violent conflicts with clan-based militias competing for territorial control, economic resources, and political influence since the collapse of the central government in 1991. While the 2012 federalization efforts like the establishment of Jubaland State have aimed to decentralize authority, promote inclusive political representation, and strengthen governance structures at regional and district levels, they have also introduced new political dynamics including disputes over power-sharing arrangements and debates over the distribution of political authority and resources among different communities.

Within this landscape, Luuq District, located within the Gedo region of Jubaland state which serves as a critical focal point for both economic activity and communal interaction has not been an exception. As home to a diverse array of Somali clans, the district has recently been characterized by a wave of political contestation and inter-clan conflicts with local communities fighting over issues of political representation/power-sharing, the equitable distribution of local administrative authority, land management, water and grazing rights, and resource (aid) management. To understand the gravity of the current situation, one must look at Luuq’s strategic significance. The district is a vital economic corridor within Gedo and the broader Jubaland State, primarily due to its proximity to the Juba River. This geographic advantage supports a robust agricultural sector and sustains the agro-pastoral livelihoods that form the backbone of the local economy.

However, the stability and security of the district deteriorated sharply in July 2024, when violent conflicts emerged between two neighboring clans. The conflict was precipitated by the long-standing grievances regarding historical injustices, land ownership, perceived unequal distribution of resources, and a struggle for the primary control of the Luuq local administration. The violence has tragically resulted in the deaths of over 30 individuals and mass displacement of at least 14,740 households (88,452 people) from their homes. The displaced families have migrated to sites/villages just outside Luuq town towards Dogob, Dhuycaley, Shadiley, Kulmiye, Yurkud and Ceelbon, while others have sought refuge within Luuq town and Xero Kowad area, along Dolow road. Despite numerous mediation attempts facilitated by traditional clan elders and the Jubaland government, the security environment remains precarious. To date, no formal or fruitful peace framework agreement has been reached. The ongoing conflict has led to the widespread destruction of private homes, retail shops, and local markets, while simultaneously obstructing the delivery of essential humanitarian aid thus contributing to widespread humanitarian needs and gaps.

This crisis is further exacerbated by environmental shocks. Recurrent cycles of drought and flooding have created a "threat multiplier" effect, interacting with existing social and political tensions. These climate-driven disasters intensify the competition over increasingly scarce resources, thereby heightening the potential for further conflict and deepening the humanitarian needs of the population.

Given these interlinked political, social, economic, security, and environmental dynamics, there is a need for a comprehensive conflict mapping and context analysis to better understand the drivers, actors, and patterns of conflict in the district.

- Rationale for the Conflict Mapping and Context Analysis

The conflict in Luuq district is non-linear and is deeply embedded in the local political economy. Given this multidimensional nature of conflict, there is a need for a comprehensive and systematic analysis that examines these dynamics in an integrated and evidence-based manner. Understanding the underlying drivers of conflict, the relationships between key actors, and the structural conditions that contribute to instability is essential before ADRO embarks on its SSF III Conciliation Initiative to ensure “Do No Harm” approach.

To this end, Access Development and Relief Organization (ADRO) through the SSF funded SF III Conciliation Initiative project, seeks to engage a qualified external consultancy firm to undertake a comprehensive Conflict Mapping and Context Analysis in Luuq district, Gedo region, Jubaland State of Somalia.

- Purpose and Objectives of the Study

  - Overall Objective

The purpose of the study is to undertake a systematic conflict mapping and context analysis in Luuq, in particular, and the greater Gedo region, in general, to generate a detailed understanding of the political, social, economic, and environmental dynamics shaping the conflict in the region. The study will identify the key drivers of conflict (social, political, economic and environmental), map relevant actors and relationships, assess current and emerging risks, and analyze the institutional and social mechanisms that influence conflict prevention and resolution. The findings will inform the design and implementation of ADRO’s conciliation and peacebuilding programmes implemented in Luuq district and the greater Gedo region of Jubaland State of Somalia

  - Specific Objectives

The specific objectives of the study include:

- Historical Analysis: Conduct a brief overview of the historical evolution of conflict dynamics in Luuq district and also give specific attention to the numerous peace-building and conflict mediation initiatives facilitated by the Jubaland government through the office of the Vice President and traditional clan elders since 2024 to present.

- Conflict Drivers Identification: Identify and analyze the structural and underlying drivers of the conflict in Luuq district and Gedo region in general such as land disputes, water and grazing rights, political/administrative representation disputes, resource (aid) management disputes, historical injustices/grievances among others.

- Actor Mapping: Map key conflict actors, their interests, influence, and relationships. This should be at context-specific level, focusing on drivers and push factors.

- Impact Assessment: Evaluate the consequences and impact of the conflict on social, economic and political relationships with specific focus on gender and age (women, girls, boys, youth and minorities).

- State the formal and traditional/informal governance systems, conflict prevention and dispute resolution mechanisms – including examining their strengths and weaknesses.

- Analyze the impact of environmental pressures and climate variability on resource competition.

- Examine gender and youth dimensions of conflict and peacebuilding – including barriers and opportunities for their participation in relevant decision-making spaces.

- Providing practical recommendations to strengthen conflict prevention and peacebuilding efforts. The recommendations are expected to cover political processes (power sharing), land dispute management, security and justice issues, as well as economic and resource management at district levels.

- Scope of Work

The study will be conducted in the Luuq district- and its surrounding settlements. The scope will encompass an in-depth assessment of political, social, security, economic, and environmental dimensions that influence conflict dynamics and social relations across Luuq district. The analysis will explore how formal governance institutions at district levels interact with informal systems of authority, including clan structures, customary institutions, and religious leadership. Attention will be given to understanding the historical and contemporary drivers of conflict, including disputes over land and natural resources, political representation, access to services, and control over economic opportunities.

Through this multi-dimensional assessment, the study will generate a detailed conflict map that identifies key actors, relationships, drivers of conflict, and potential entry points for conflict prevention and peacebuilding in the district. As part of this, the consultant will examine the following dimensions within Luuq District and the greater Gedo region

| ## Dimensions | ## Key Areas of Focus | ## Duration |
| --- | --- | --- |
| ## Political and Governance Dynamics | ## The study will examine governance structures at the district level to understand how political authority and administrative responsibilities are organized and exercised within Luuq district. Attention will be given to the relationships between the federal government of Somalia, Jubaland State and Luuq district authorities, and how these relationships influence political representation, accountability, and decision-making processes. In addition, the study will explore the interaction between formal governance institutions at the district level and informal authority systems, including clan elders and religious leaders as these traditional structures often play a critical role in maintaining social order and mediating conflicts within communities. |  |
| ## Clan Relations and Social Dynamics | ## The study will analyse the role of clan and sub-clan structures in shaping social relations, political alliances, and conflict dynamics within the district. Clan identity remains a key factor influencing access to resources, representation in governance institutions, and the management of disputes between communities. It will examine historical inter-clan relationships, territorial claims, and existing grievances that may contribute to tensions or conflict between different groups. Particular focus will be given to the relationships between the Reer Hassan, Gabaweyn, and Ma’alin Wayne; and other minority clans. |  |
| Security and Armed Actors | ## The study will assess the security landscape of Luuq district by identifying the various security actors operating within the region and examining their roles, influence, and interactions with local communities so as to understand how they shape local stability. |  |
| ## Resource-based Conflicts | ## The study will examine patterns of competition over natural resources in Luuq district, particularly disputes related to land ownership, water access, and grazing areas. These resources are central to the livelihoods of agricultural and pastoral communities, and competition over their use can contribute to tensions between different groups. |  |
| Socioeconomic Drivers | The consultancy will analyse the socioeconomic conditions that shape conflict dynamics in Luuq district, including levels of poverty, unemployment, and access to livelihood opportunities. Economic hardship and limited access to resources can contribute to frustration and social tension, particularly among youth who may face significant barriers to employment and economic participation. |  |
| Gender and Social Inclusion | The consultancy will analyse the differential impacts of conflict on women, youth, and marginalized groups within the Luuq district. Conflict and insecurity often affect social groups in distinct ways, influencing access to resources, participation in decision-making processes, and exposure to violence or displacement. The study will examine how these impacts are experienced across different segments of society. In addition, the analysis will explore the roles played by women and youth in peacebuilding and conflict resolution processes. |  |

- Methodology

The consultant is expected to adopt a mixed-method approach that combines both quantitative and qualitative methods to generate a comprehensive understanding of conflict dynamics in Luuq district and the greater Gedo region. The study should begin with an extensive desk review of existing literature, reports, policy documents, and previous conflict assessment reports related to governance, security, social dynamics, and environmental pressures in the region. This review will help establish a contextual foundation and guide the design of field research activities.

Primary data collection will be conducted through household’s questionnaire, key informant interviews and focus group discussions with a wide range of stakeholders, including communities, community leaders, government officials, civil society organizations, women groups, peace committees, natural resource committees, youth representatives, and other relevant actors. In addition, the study will apply analytical tools such as stakeholder mapping, conflict tree analysis, power-interest analysis, and conflict timeline mapping to identify relationships between actors, drivers of conflict, and potential entry points for peacebuilding. The findings will be validated through consultations with key stakeholders to ensure the accuracy, credibility, and relevance of the analysis.

- Expected Deliverables

The successful consultancy firm is expected to deliver the following key deliverables during the assignment;

- Inception Report: Outlining the proposed methodology, research design, sampling approach, data collection tools, and detailed workplan.

- Draft Conflict Analysis Report with initial findings of the conflict mapping, key drivers of conflict, stakeholder mapping, and preliminary recommendations.

- Final Conflict Mapping and Context Analysis Report that present a comprehensive assessment of conflict dynamics in Luuq district, supported by evidence and detailed recommendations.

- Presentation and validation of findings: Presentation of findings of the study to stakeholders through a dissemination workshop that will provide an opportunity to discuss the results and gather feedback.

- Duration of the Assignment

The consultancy assignment is expected to be completed within a period of 3 weeks (21 days) from the date of contract signing.

| ## No | ## Key activities | ## Duration |
| --- | --- | --- |
| ## 1 | ## Inception and Planning | ## 3 days |
| ## 2 | ## Desk Review and Context Analysis | ## 3 days |
| ## 3 | ## Field Data Collection | ## 7 days |
| ## 4 | ## Data Analysis and Conflict Mapping | ## 3 days |
| ## 5 | ## Draft Report Preparation | ## 3 days |
| ## 6 | ## Validation and Finalization | ## 2 days |

- Qualifications of the Consultancy Firm

The consultancy firm should meet the following minimum qualifications:

- Proven institutional experience of at least 5-7 years in conducting conflict and climate analysis, peacebuilding research, governance assessments, or political economy analysis in fragile and conflict-affected contexts.

- Demonstrated experience implementing similar assignments such as conflict mapping, social cohesion studies, or context analyses for international NGOs, UN agencies, government institutions, or development partners.

- Strong technical expertise in conflict analysis methodologies, including stakeholder mapping, conflict tree analysis, political economy analysis, and risk assessment.

- Demonstrated experience conducting quantitative and qualitative research, including household level assessments, key informant interviews, focus group discussions, and participatory community consultations.

- Proven knowledge of Somalia’s political, governance, and security landscape, particularly the dynamics within Gedo region and Jubaland state of Somalia.

- Ability to engage diverse stakeholders, including government institutions, community leaders, civil society organizations, women groups, and youth representatives.

- Strong analytical and report writing capacity, with a track record of producing high-quality analytical reports and policy-oriented publications.

- Demonstrated commitment to ethical research practices, including conflict-sensitive approaches, informed consent, and the application of Do No Harm principles.

- Proposal Submission Requirements

## Interested consultancy firms are invited to submit a comprehensive proposal outlining their technical expertise, understanding of the assignment, methodology and approach to undertake the assignment. The submission should include the following documents:

- Technical Proposal: A detailed technical proposal describing the firm’s understanding of the assignment, the proposed approach, and the methodology to be used for conducting the conflict mapping and context analysis.

- Detailed Methodology: A clear description of the proposed research methodology, including data collection methods, analytical tools and stakeholder engagement strategies.

- Workplan and Timeline: A proposed workplan outlining the key phases of the assignment, expected activities, and timeline for completing each deliverable.

- Company Profile: A brief profile of the consultancy firm highlighting its institutional experience, core areas of expertise, and relevant experience in conducting similar assignments.

- Curriculum Vitae of Key Team Members: Updated CVs of all key personnel proposed for the assignment, clearly outlining their qualifications, relevant experience, and roles.

- Financial Proposal: A detailed financial proposal indicating the total cost of the consultancy, including professional fees, operational costs, and any other expenses associated with the assignment.

- References from Previous Assignment: Contact details of at least three to five references from previous clients or organizations for whom the consultancy firm has conducted similar assignments.

- How to Apply

Interested firms should submit their complete RFP, technical and financial proposals and all other requested documents to this email address procurement@adro.org clearly marking the subject line “Conflict Mapping and Context Analysis for Luuq District” no later than 13th May 2026 at 11:59PM.